## Sheet2
Build Type (GL) | Milestone / Subtask Field | Start Month | Duration / Cycle Time
BTS / Build to Colocate | ENGINEERING RELEASE | 0 | 1 DAY
BTS / Build to Colocate | CANDIDATE SUBMITTED | 1 | 8 WEEKS
BTS / Build to Colocate | RF ACCEPTED AND RANKED | 1 | 2 WEEKS
BTS / Build to Colocate | SUBMIT RFDS COMPLETED | 3 | 2 WEEKS
BTS / Build to Colocate | RFDS REVIEWED BY EE | 3 | 3 DAYS
BTS / Build to Colocate | AE SITE WALK | 7 | 2 WEEKS
BTS / Build to Colocate | 1A/2C SURVEY COMPLETED | 7 | 2 WEEKS
BTS / Build to Colocate | SLA LEASE EXECUTED | 3 | 24 WEEKS
BTS / Build to Colocate | ENVIROMENTAL DUE DILLIGENCE MILESTONE | 8 | 12 WEEKS
BTS / Build to Colocate | FINAL CDS APPROVED | 11 | 2 WEEKS
BTS / Build to Colocate | ZONING APPROVED | 10 | 12 WEEKS
BTS / Build to Colocate | REGULATORY CONSTRUCTION MILESTONE | 10 | 24 WEEKS
BTS / Build to Colocate | ALL PERMITS APPROVED | 13 | 8 WEEKS
BTS / Build to Colocate | TENANT READY | 17 | 4 WEEKS
BTS / Build to Colocate | REAL ESTATE RELEASE | 16 | 4 WEEKS
BTS / Build to Colocate | REAL ESTATE COMPLETED (REC) MILESTONE | 18 | 2 WEEKS
BTS / Build to Colocate | CONSTRUCTION STARTED | 18 | 8 WEEKS
Colocation (New Build) / Water Tank | Milestone / Subtask Field | Start Month | Duration / Cycle Time
Colocation (New Build) / Water Tank | ENGINEERING RELEASE | 0 | 1 DAY
Colocation (New Build) / Water Tank | CANDIDATE SUBMITTED | 1 | 8 WEEKS
Colocation (New Build) / Water Tank | RF ACCEPTED AND RANKED | 1 | 2 WEEKS
Colocation (New Build) / Water Tank | SUBMIT RFDS COMPLETED | 3 | 2 WEEKS
Colocation (New Build) / Water Tank | RFDS REVIEWED BY EE | 3 | 3 DAYS
Colocation (New Build) / Water Tank | AE SITE WALK | 4 | 2 WEEKS
Colocation (New Build) / Water Tank | 1A/2C SURVEY COMPLETED | 4 | 2 WEEKS
Colocation (New Build) / Water Tank | SLA LEASE EXECUTED | 4 | 24 WEEKS
Colocation (New Build) / Water Tank | ENVIROMENTAL DUE DILLIGENCE MILESTONE | 6 | 12 WEEKS
Colocation (New Build) / Water Tank | FINAL CDS APPROVED | 7 | 2 WEEKS
Colocation (New Build) / Water Tank | ZONING APPROVED | 6 | 12 WEEKS
Colocation (New Build) / Water Tank | REGULATORY CONSTRUCTION MILESTONE | 5 | 24 WEEKS
Colocation (New Build) / Water Tank | ALL PERMITS APPROVED | 11 | 8 WEEKS
Colocation (New Build) / Water Tank | TENANT READY | 13 | 4 WEEKS
Colocation (New Build) / Water Tank | REAL ESTATE RELEASE | 12 | 4 WEEKS
Colocation (New Build) / Water Tank | REAL ESTATE COMPLETED (REC) MILESTONE | 14 | 2 WEEKS
Colocation (New Build) / Water Tank | CONSTRUCTION STARTED | 15 | 8 WEEKS